CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

Automatic Attendance System Based on Real-Time Location and Face Recognition

INSTRUCTOR: BÙI THỊ LOAN

CLASS: SEP490_G16

Team Members:

| - Trần Long Khánh | HE176617 |
| --- | --- |
| - Nguyễn Đình Dũng | HE176518 |
| - Hà Việt Hiếu | HE176256 |
| - Nguyễn Văn Đạt | HE176009 |
| - Kiều Thị Ngọc Dung | HE171203 |

Hanoi, June 2025

Table of Contents

Definitions & Acronyms	4

I. Record of Changes	5

II. Project Management Plan	6

1. Overview	6

1.1 Scope & Estimation	6

1.2 Project Objectives	11

1.3 Project Risks	11

2. Management Approach	12

2.1 Project Process	12

2.2 Quality Management	13

2.2.1 Defect Prevention	13

2.2.2 Coding	13

2.2.3 Reviewing	14

2.2.4 Unit Testing	14

2.2.5 Integration Testing	14

2.2.6 System Testing	14

2.3 Training Plan	15

3. Project Deliverables	16

4. Responsibility Assignments	18

4.1 Teams and Structures	18

4.2 Role & Responsibilities	18

5. Project Communications	20

6. Configuration Management	21

6.1 Document Management	21

6.2 Source Code Management	21

6.2.1. Convention	22

6.2.2.Management	22

6.3 Tools & Infrastructures	22

List of Figures

| Figure No. | Title | Page |
| --- | --- | --- |
| Figure 1 | Development process of the iterative and incremental model | 13 |
| Figure 2 | Team Structure | 17 |
| Figure 3 | Source code and version control workflow | 21 |

Table 1 - List of Figures

List of Tables

| Table No. | Title | Page |
| --- | --- | --- |
| Table 1 | List of Figures | 3 |
| Table 2 | List of Tables | 3 |
| Table 3 | Definitions & Acronyms | 4 |
| Table 4 | Record of Changes | 5 |
| Table 5 | WBS Breakdown | 6 |
| Table 6 | Project Objectives | 11 |
| Table 7 | Project Risks | 11 |
| Table 8 | Testing Process | 14 |
| Table 9 | Defect Classification | 15 |
| Table 10 | Project Training Plan | 15 |
| Table 11 | Project Deliverables | 16 |
| Table 12 | Responsibility Assignment | 18 |
| Table 13 | Project Communications | 20 |
| Table 14 | Document Management | 21 |
| Table 15 | Tools & Infrastructures | 22 |

Table 2 - List of Tables

# Definitions & Acronyms

| No | Acronyms & Abbreviations | Definition |
| --- | --- | --- |
| 1 | AAS | Automatic Attendance System |
| 2 | API | Application Programming Interface |
| 3 | BLE | Bluetooth Low Energy |
| 4 | PMP | Project Management Plan |
| 5 | WBS | Work Breakdown Structure |
| 6 | SRS | Software Requirements Specification |
| 7 | SDS | Software Design Specification |
| 8 | UI | User Interface |
| 9 | UX | User Experience |
| 10 | OWASP | Open Web Application Security Project |

Table 3 - Definitions & Acronyms

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 27/05/2025 | A | DungND | Added initial draft of Project Management Plan (PMP) structure. |
| 21/06/2025 | A | DungND | Added detailed Work Breakdown Structure (WBS) and project schedule. |
| 22/06/2025 | A | DungND | Added Communication Plan and Responsibility Assignment Matrix. |
| 19/08/2025 | M | DungND | Modified project schedule (updated milestones and deadlines). |
| 20/08/2025 | M | DungND | Modified Responsibility Assignment (RACI) and Communication Plan. |

*A - Added M - Modified D - Deleted

Table 4 - Record of Changes

# II. Project Management Plan

## 1. Overview

This chapter establishes the Project Management Plan for the Automatic Attendance System (AAS). The plan includes the project’s overall scope and effort estimation, the overall management model (Iterative & Incremental), responsibilities at a personal level, risk evaluation, and leverage. This chapter ensures the production and delivery of high-quality results at any phase of project execution.

### 1.1 Scope & Estimation

We categorize WBS items into three levels of complexity:

- Simple = 1 man-day

- Medium = 3 man-days

- Complex = 8 man-days

The total effort is estimated accordingly for each item.

| WBS ID | WBS Item | Task Description | Complexity | Effort (days) |
| --- | --- | --- | --- | --- |
| I | Iteration 1 – Initiation & Foundational Research (Week 1–2) |  |  | 42 |
| 1.1 | Requirement Analysis |  |  |  |
| 1.1.1 | Report 1 – Introduction (outline) | Draft structure, scope, team, rationale | Medium | 3 |
| 1.1.2 | Report 2 – PMP (outline) | Timeline, resources, milestones, risks | Medium | 3 |
| 1.1.3 | Stakeholder Workshop | Goals, constraints, risk assumptions | Medium | 3 |
| 1.1.4 | Draft Use Case List | Initial functional use cases (no fixed count) | Medium | 3 |
| 1.2 | Design |  |  |  |
| 1.2.1 | Architecture Approach | Select initial architecture for app, web, backend | Medium | 3 |
| 1.3 | Coding |  |  |  |
| 1.3.1 | Backend Bootstrap | Repos, envs, CI/CD, base DB schema | Complex | 8 |
| 1.3.2 | BLE Research POC | Scan/broadcast prototype & limitations | Complex | 8 |
| 1.3.3 | Face Recognition POC | On-device FR with liveness check | Complex | 8 |
| 1.4 | Testing |  |  |  |
| 1.4.1 | Pipeline Smoke Tests | CI/CD health checks & API ping | Medium | 3 |
| II | Iteration 2 – System Design & Initial Prototyping (Week 3–4) |  |  | 28 |
| 2.1 | Requirement Analysis |  |  |  |
| 2.1.1 | Finalize Use Cases | Refine functional and non-functional requirements | Medium | 3 |
| 2.1.2 | Data Model Draft | Initial ERD, attributes, relationships | Medium | 3 |
| 2.2 | Design |  |  |  |
| 2.2.1 | Low-Fidelity Wireframes | Sketch basic UI flows | Medium | 2 |
| 2.2.2 | System Sequence Diagrams | Capture user-system interaction | Medium | 2 |
| 2.2.3 | Technical Stack Validation | Validate frameworks & SDKs | Medium | 2 |
| 2.3 | Coding |  |  |  |
| 2.3.1 | API Skeleton | Define endpoints, controllers | Medium | 3 |
| 2.3.2 | Web Portal Skeleton | Initial admin dashboard structure | Medium | 3 |
| 2.3.3 | Mobile App Skeleton | Initial navigation, screens | Medium | 3 |
| 2.4 | Testing |  |  |  |
| 2.4.1 | Design Walkthrough | Validate mockups with peers | Simple | 2 |
| 2.4.2 | Prototype Demo | Present basic navigation flow | Simple | 2 |
| III | Iteration 3 – Core Backend & API Development (Week 5–6) |  |  | 40 |
| 3.1 | Requirement Analysis |  |  |  |
| 3.1.1 | API Contract Workshop | Finalize request/response specs | Medium | 2 |
| 3.2 | Design |  |  |  |
| 3.2.1 | DB Schema Finalization | Normalize, index, constraints | Medium | 3 |
| 3.2.2 | API Documentation Draft | Swagger/OpenAPI setup | Medium | 2 |
| 3.3 | Coding |  |  |  |
| 3.3.1 | Authentication Service | JWT setup | Complex | 6 |
| 3.3.2 | User Management APIs | CRUD for user accounts | Medium | 4 |
| 3.3.3 | Attendance APIs | Endpoints for check-in/out | Medium | 4 |
| 3.3.4 | BLE Integration Service | Link with the BLE scanner | Complex | 6 |
| 3.4 | Testing |  |  |  |
| 3.4.1 | Unit Test Coverage | Services and API endpoints | Medium | 4 |
| 3.4.2 | Postman Collection | Integration checks | Simple | 3 |
| IV | Iteration 4 – Mobile Application Development (Week 7–8) |  |  | 38 |
| 4.1 | Requirement Analysis |  |  |  |
| 4.1.1 | Mobile UX Research | Validate flows with peers | Medium | 2 |
| 4.1.2 | Accessibility Requirements | Draft accessibility standards | Medium | 2 |
| 4.2 | Design |  |  |  |
| 4.2.1 | High-Fidelity Mobile Mockups | Polished Figma screens | Medium | 3 |
| 4.2.2 | Mobile Navigation Flow | Final tab, drawer, deep links | Medium | 2 |
| 4.3 | Coding |  |  |  |
| 4.3.1 | Login & Registration | Mobile auth screens | Medium | 3 |
| 4.3.2 | Attendance Check-in | BLE + Face Recognition trigger | Complex | 6 |
| 4.3.3 | Attendance History | List & details | Medium | 3 |
| 4.4 | Testing |  |  |  |
| 4.4.1 | Emulator Testing | Android basic tests | Simple | 3 |
| 4.4.2 | Field Test (Pilot) | Try with real devices | Complex | 5 |
| V | Iteration 5 – Web Portal Development (Week 9–10) |  |  | 33 |
| 5.1 | Requirement Analysis |  |  |  |
| 5.1.1 | Admin Needs Workshop | Reports, filtering | Medium | 2 |
| 5.1.2 | Security Requirements | RBAC, logging | Medium | 2 |
| 5.2 | Design |  |  |  |
| 5.2.1 | Admin Dashboard Wireframes | Layout, cards, filters | Medium | 2 |
| 5.2.2 | Reporting Templates | Export formats | Medium | 2 |
| 5.3 | Coding |  |  |  |
| 5.3.1 | Dashboard Home | Stats, charts | Medium | 3 |
| 5.3.2 | Attendance Logs View | Search, filter | Medium | 3 |
| 5.3.3 | User Management Page | List, add, deactivate | Medium | 3 |
| 5.3.4 | Role Management | RBAC setup | Medium | 3 |
| 5.4 | Testing |  |  |  |
| 5.4.1 | Browser Testing | Chrome, Firefox, Edge | Medium | 3 |
| 5.4.2 | Security Testing | Pen-test basics | Complex | 5 |
| VI | Iteration 6 – Integration & System Testing (Week 11–12) |  |  | 35 |
| 6.1 | Requirement Analysis |  |  |  |
| 6.1.1 | Integration Scenarios | Define cross-module flows | Medium | 2 |
| 6.1.2 | Test Data Requirements | Seed realistic datasets | Medium | 2 |
| 6.2 | Design |  |  |  |
| 6.2.1 | Test Architecture | CI/CD automated testing plan | Medium | 3 |
| 6.3 | Coding |  |  |  |
| 6.3.1 | API Gateway Setup | Central entry point | Complex | 5 |
| 6.3.2 | Notification Service | Email/SMS microservice | Medium | 4 |
| 6.4 | Testing |  |  |  |
| 6.4.1 | System Integration Tests | End-to-end validation | Complex | 6 |
| 6.4.2 | Load Testing | Simulate 500 concurrent users | Complex | 6 |
| VII | Iteration 7 – UAT & Pilot Deployment (Week 13–14) |  |  | 32 |
| 7.1 | Requirement Analysis |  |  |  |
| 7.1.1 | UAT Criteria | Define entry/exit conditions | Medium | 2 |
| 7.2 | Design |  |  |  |
| 7.2.1 | UAT Scripts | Draft scenarios for testers | Medium | 3 |
| 7.3 | Coding |  |  |  |
| 7.3.1 | Deployment Scripts | Docker manifests | Medium | 3 |
| 7.3.2 | Monitoring Setup | Logging & dashboards | Medium | 3 |
| 7.4 | Testing |  |  |  |
| 7.4.1 | UAT Execution | Run with 10 pilot users | Complex | 6 |
| 7.4.2 | UAT Feedback Analysis | Summarize gaps | Medium | 3 |
| VIII | Iteration 8 – Closure & Final Delivery (Week 15) |  |  | 14 |
| 8.1 | Project Closure |  |  |  |
| 8.1.1 | Prepare Final Presentation Slides | Build a defense slide deck | Simple | 1 |
| 8.1.2 | Demo Video | Record and edit the final demo | Medium | 2 |
| 8.1.3 | Rehearsal Defense | Conduct a mock defense session | Simple | 1 |
| 8.1.4 | Documentation Review | Final check of all deliverables | Medium | 2 |
| 8.1.5 | Final Project Report | Start Report 7 – Final Project Report | Complex | 8 |

| Total Estimated Effort (man-days) |  |  |  | 280 |
| --- | --- | --- | --- | --- |

Table 5 - WBS Breakdown

### 1.2 Project Objectives

| # | Testing Stage | Test Coverage | Unit | Planned | Actual | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Effort Usage | 100% of planned man-days | Person-days | 280 | 300 | Ensure resource usage matches project estimates. |
| 2 | Reviewing | 100% of documentation reviewed | No. of defects | ≤10 | N/A | Completeness & consistency of SRS, SDS, PMP, UI/UX artifacts. |
| 3 | Unit Test | All major functions and components | No. of defects | ≤10 | N/A | Verify Authentication, Settings, Device, and Session modules. |
| 4 | Integration Test | All integrated modules | No. of defects | ≤15 | N/A | Test mobile ↔ backend ↔ web flows, BLE/Wi-Fi data, face-ID integration. |
| 5 | System Test | 100% of system functionality | No. of defects | ≤20 | N/A | Cover login, attendance capture, offline sync, reporting, threshold alerts. |
| 6 | Acceptance Test | Client-defined critical functionalities | No. of defects | ≤20 | N/A | Final stakeholder sign-off on mobile app, web portal, and analytics. |

Table 6 - Project Objectives

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Learning curve for new technologies (BLE, Wi-Fi fingerprinting) | High | High | Organize early training & proof-of-concept in Iteration 1–2; assign “technology champions” to mentor peers. |
| 2 | Limited availability or unexpected absence of part-time members | High | Medium | Maintain ~20% effort buffer in each Iteration plan; cross-train members; rotate weekly “backup” roles. |
| 3 | Scope creep from stakeholder change requests | Medium | High | Apply formal change control: New requests must undergo impact analysis and be reviewed at the end of each Iteration. |
| 4 | Integration failures (mobile ↔ backend ↔ web portal) | High | Medium | Build integration stubs & automated checks starting Iteration 2; schedule dedicated “integration checkpoints” in subsequent Iterations. |
| 5 | Device compatibility issues (Android versions, BLE chipset variations) | Medium | Medium | Document supported device list in SRS; provide fallback manual check-in option; validate across devices in Iteration 3–4. |
| 6 | Security vulnerabilities (unauthorized access, data leaks) | High | Low | Conduct threat modeling in Iteration 4; perform code/security scans regularly; adopt OWASP Mobile Top 10 practices. |
| 7 | Performance degradation under heavy load | Medium | Medium | Define performance benchmarks in Iteration 5; perform load testing & optimize hotspots before Iteration 7–8. |
| 8 | Data privacy & compliance risks (location & biometric data handling) | High | Low | Implement encryption at rest/in transit; anonymize logs; review compliance with legal/IT security team in Iteration 4–5. |

Table 7 - Project Risks

## 2. Management Approach

### 2.1 Project Process

In this project, we apply the Iterative and Incremental development model. The main principle of this model is to deliver the system in a sequence of iterations, where each iteration goes through the essential phases: Requirement Analysis → Design → Coding → Testing.

With this approach, the Automatic Attendance System (AAS) is gradually built and refined over multiple iterations. Lessons learned and feedback from earlier iterations are incorporated into later ones, ensuring continuous improvement and higher quality of the final product.

Each iteration delivers a working subset of features — for example:

- Iteration 1 focuses on core user authentication and basic attendance recording.

- Iteration 2 introduces BLE data capture and device management.

- Iteration 3 integrates face recognition for identity validation.

- Iteration 4 onward improves reporting, analytics, and system performance.

This approach ensures adaptability to requirement changes, risk reduction through early validation, and steady progress toward the complete system.

Figure 1: Development process of the iterative and incremental model

### 2.2 Quality Management

#### 2.2.1 Defect Prevention

- Any defect discovered during Requirement, Design, Coding, or Testing must be immediately communicated to the responsible member.

- Defects are evaluated by severity and impact (e.g., “Does the defect affect critical attendance tracking or data accuracy?”).

- Clear deadlines for defect resolution are assigned.

- Preventive actions (such as design reviews, static code checks, and pair programming) are used to minimize future defects.

#### 2.2.2 Coding

- Developers follow established Java/C#/React coding conventions to ensure readability and maintainability.

- Each implemented feature is peer-reviewed and accompanied by unit tests.

- Code review is mandatory before merging into the main branch to maintain system stability.

- Developers must keep local codebases updated to avoid conflicts and ensure early detection of issues.

- Security and privacy practices (e.g., encryption, OWASP guidelines) are enforced during development.

#### 2.2.3 Reviewing

- Reviews must remain objective, focusing solely on code or documentation quality, not personal bias.

- Findings (defects, gaps, ambiguities) are logged in GitHub Project with severity, priority, and owner details.

- Assigned members are responsible for promptly addressing review findings and confirming fixes.

- Major artifacts subject to review: Software Requirement Specification (SRS), Software Design Specification (SDS), Project Management Plan (PMP), UI/UX wireframes.

#### 2.2.4 Unit Testing

- Unit tests are written for all critical modules: Authentication, Settings, Device management, Attendance capture, and Session handling.

- Test cases must be carefully designed to cover normal, boundary, and exceptional cases.

- Results and discovered defects are logged with priority in the GitHub Project.

- The developer responsible must resolve unit test defects immediately.

#### 2.2.5 Integration Testing

- Integration test cases validate the interaction between the mobile app, the backend API, and the web portal.

- Critical flows: BLE scanning data → backend API → attendance records update → web reporting.

- The faceid recognition module is tested with backend session validation.

- Defects found are logged with priority; responsible members must address them quickly.

- Iterations include dedicated integration checkpoints to ensure modules work smoothly together.

#### 2.2.6 System Testing

- System-level test cases validate 100% of functional and non-functional requirements.

- Coverage includes login, attendance capture (BLE, Wi-Fi, FaceID), offline synchronization, reporting dashboards, threshold alerts, and administrative controls.

- System testing also validates compliance with performance, privacy, and security requirements.

- Defects are logged in GitHub Project, prioritized, and resolved before moving to Acceptance Testing.

- System testing ensures the solution can operate in real-world environments with multiple concurrent users and diverse device types.

| Testing Method | Target |
| --- | --- |
| Unit Test | Validate each module in isolation (Auth, Attendance, Device, Session); ensure ≥ 95% coverage for core business logic. |
| Integration Test | Verify end-to-end data flows across mobile ↔ backend ↔ web; detect mismatches in BLE scanning, FaceID, and API connections. |
| System Test | Execute all user stories (login, check-in, offline sync, reporting); confirm the system meets both functional and non-functional requirements. |
| Performance Test | Ensure the system handles peak load (≥ 200 devices performing BLE/FaceID scans concurrently) with response time under 2 seconds. |
| Usability Test | Observe real users in classroom/event scenarios; collect feedback to refine UI/UX before final acceptance. |

Table 8 - Testing Process

| Defect Label | Description | Action |
| --- | --- | --- |
| CRITICAL | Breaks core attendance functionality (e.g., app crash, data loss, security breach, inability to check-in). | Stop all new feature development; assign top priority and fix immediately. |
| MAJOR | Severely impacts key flows (e.g., authentication failures, BLE/FaceID not working, unsynchronized backend data). | Block release until resolved; address within the current iteration. |
| MINOR | Non-critical issues that reduce user experience (e.g., wrong error messages, slow sync, minor UI glitches). | Log in backlog; schedule fix in the next iteration based on priority. |
| TRIVIAL | Cosmetic or documentation issues (e.g., typos, layout misalignment, minor log inaccuracies). | Defer to future maintenance; record for reference but no immediate fix required. |

Table 9 - Defect Classification

### 2.3 Training Plan

To ensure all team members can contribute effectively, we’ve scheduled targeted training on our core technologies, processes, and tools. Each session is led by the in-team expert for that topic, with mandatory attendance unless explicitly waived.

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Iterative & Incremental Fundamentals | All members | Iteration 1, Day 1 (½ day) | Mandatory |
| Git & GitHub Workflows | All members | Iteration 1, Week 2 (1 day) | Mandatory |
| BLE Propagation & Wi-Fi Fingerprinting | Backend & Mobile devs | Iteration 1, Week 3 (2 days) | Mandatory |
| On-Device Face Recognition Integration | Mobile devs | Iteration 1, Week 3 (1 day) | Mandatory |
| Cross-Platform Mobile App Development | Mobile devs | Iteration 2, Week 1 (2 days) | Mandatory |
| React Web Portal | Web devs | Iteration 2, Week 2 (2 days) | Mandatory |
| Unit & Integration Testing Frameworks | All members | Iteration 3, Week 1 (1 day) | Mandatory |

Table 10 - Project Training Plan

## 3. Project Deliverables

| Deliverable | Due Date | Notes |
| --- | --- | --- |
| Report 1 – Project Introduction | 25/05/2025 | Provides project background, objectives, scope, high-level architecture, and main use cases. |
| Report 2 – Project Management Plan | 08/06/2025 | Defines schedule, resources, risk & communication plans, and iteration breakdowns. |
| Project Repository & CI/CD Pipeline Setup | 08/06/2025 | Configured GitHub repo with automated build, test, lint, and quality checks (SonarQube, CI/CD pipeline). |
| Research Paper – BLE & Wi-Fi Propagation Study | 22/06/2025 | Summarizes pilot measurements, propagation algorithms, and fingerprinting experiments. |
| Report 3 – Software Requirements Specification (SRS) | 22/06/2025 | Functional & non-functional requirements, detailed use cases, and traceability matrix. |
| Report 4 – Software Design Specification (SDS) | 06/07/2025 | Includes architecture diagrams, data models, UI wireframes, and security design. |
| MVP Release v1.0 – Mobile & Web Portal | 18/07/2025 | First usable increment: authentication, device registration, attendance capture, and dashboard. |
| Incremental Release v2.0 – Enhanced Features | 04/08/2025 | Adds advanced reporting, BLE+FaceID hybrid attendance verification, role-based access control, and refined UI/UX. |
| Report 5 – Test Documentation | 12/08/2025 | Contains test plan, test cases, and results for unit, integration, system, performance, and usability tests. |
| Report 6 – User Guides & API Documentation | 14/08/2025 | End-user manuals and API reference with examples, workflows, screenshots, and troubleshooting. |
| Final Project Report & Presentation | 17/08/2025 | Consolidates all reports, source code, presentation slides, and lessons learned. |
| Project Archive & Handover Package | 17/08/2025 | Final GitHub release tag, deployment scripts, maintenance plan, and support SLA for transition. |

Table 11 - Project Deliverables

## 4. Responsibility Assignments

### 4.1 Teams and Structures

Figure 2:Team Structure

### 4.2 Role & Responsibilities

The table below lists the responsibilities of a person in a specific role. Each role carries different

responsibilities related to the team and the assignment tasks.

(D~Do; R~Review; S~Support; I~Informed)

| # | Responsibility | KhanhNT | DungND | HieuHV | DatNV | DungKTN |
| --- | --- | --- | --- | --- | --- | --- |
| I. Planning |  |  |  |  |  |  |
| 1 | Choose technology & languages | D | S | S | S | I |
| 2 | Create a project schedule | D | R | I | I | I |
| 3 | Choose a process model | D | R | I | I | I |
| II. Research & Experiments |  |  |  |  |  |  |
| 4 | BLE propagation experiments & paper | D | S | S | S | S |
| 5 | Wi-Fi fingerprinting experiments & paper | S | S | D | S | S |
| III. Documentation & Design |  |  |  |  |  |  |
| 6 | Report 1 – Project Introduction | R | D | I | I | I |
| 7 | Report 2 – Project Management Plan | R | D | I | I | I |
| 8 | Report 3 – Software Requirements (SRS) | R | D | S | S | D |
| 9 | Report 4 – Software Design (SDS) | R | S | D | D | I |
| 10 | UI/UX design for mobile & web | R | D | I | I | I |
| 11 | User guides & API documentation | R | D | I | D | D |
| IV. Development |  |  |  |  |  |  |
| 12 | Implement backend modules (Auth, Device, Settings) | S | I | S | D | I |
| 13 | Implement mobile‐app modules | D | I | S | S | I |
| 14 | Implement web‐portal modules (React) | I | D | S | S | D |
| 15 | Design the database schema | R | S | D | D | I |
| V. Testing |  |  |  |  |  |  |
| 16 | Test planning (unit, integration, system, UAT) | S | D | S | S | D |
| 17 | Unit testing | S | D | S | S | D |
| 18 | Integration testing | S | S | S | S | D |
| 19 | System & performance testing | S | D | S | S | D |
| 20 | Usability & acceptance testing | R | S | S | S | D |
| VI. Deployment & Handover |  |  |  |  |  |  |
| 21 | MVP release & feedback collection | R | S | S | D | I |
| 22 | Final release, documentation handover & archive | R | D | S | S | I |

Table 12 - Responsibility Assignment

## 5. Project Communications

| # | Communication Item | Who / Target | Purpose | When / Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- | --- |
| 1 | Daily Meeting | All team members | Share progress, clarify tasks, raise blockers. | Every workday at 07:00 | Google Meet (15 min) |
| 2 | Weekly Supervisor Meeting | Team members & Instructor | Review overall progress, discuss issues, obtain feedback. | Every Tuesday at 13:00 | In-class or Google Meet |
| 3 | Iteration Planning | Team members | Plan upcoming iteration based on WBS deliverables, allocate responsibilities. | At the start of each iteration | Google Meet (60 min) |
| 4 | Iteration Review & Retrospective | Team members & Instructor | Demo completed deliverables (Review); reflect on what went well and what to improve (Retro). | End of each iteration | Google Meet (Review 45 min + Retro 45 min) |
| 5 | Backlog / Task Refinement | Team members | Update priorities, clarify requirements, refine tasks from WBS. | Mid-iteration or as needed | GitHub Issues & Project Board |

Table 13 - Project Communications

## 6. Configuration Management

### 6.1 Document Management

Our team utilizes Google Drive to organize and maintain all project documentation. This cloud service enables multiple users to work on the same files at the same time, with every change automatically saved and versioned.

Within our Drive, we structure materials into three key folders: Documents, which houses all formal deliverables and supplementary files; Management, where we keep records of team roles, workflows, and project operations; and Testing, dedicated to storing test plans, logs, and reports.

We author our reports and spreadsheets directly in Google Docs and Google Sheets, allowing everyone on the team to collaborate seamlessly and stay synchronized.

Link to Driver:

| Tool | Activity |
| --- | --- |
| Google Drive | Store all documents |
| Googles Docs | Document Report, User Guide |
| Google Sheet | Project Tracking, Project Weekly, Issues Report |
| Canva | Slide Presentation |
| Figma | Design Components, Screens |
| Draw.io / Lucid Chart | Diagrams |

Table 14 - Document Management

### 6.2 Source Code Management

Team members use GitHub for source code and version control following this workflow:

Figure 3: Source code and version control workflow

#### 6.2.1. Convention

- All coding branches must be reviewed by team developers before merging into

the main branch.

- Team members are only allowed to commit code to the local repository.

- Code must be fully tested and can run well on the local side before sending pull

requests to the master repository for finished implementations.

#### 6.2.2.Management

- Source code managed by GitHub.

- The technique leader is the person who must review carefully before merging the

code of team members.

- Only team members and mentors can access the repository on GitHub.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Android Java, C#/ASP.NET, Javascript |
| Database | PostgreSQL |
| IDEs/Editors | Visual Studio Code, Jetbrain Rider, Android Studio |
| Diagramming | DrawIO, PlantUML |
| Documentation | Google Docs/Sheets |
| Version Control | Github (Source Codes), Google Drive (Documents) |
| Deployment server | Cloudflare Hosting |

Table 15 - Tools & Infrastructures