## WBS
PROJECT WORK BREAKDOWN STRUCTURE
No | WBS Items | Complexity | Planned | Status
1 | Project Initialization
2025-01-01 | Define project scope | Medium | Iter 1 | Done
2025-02-01 | Identify stakeholders | Low | Iter 1 | Done
2025-03-01 | Create project charter | Medium | Iter 1 | Done
2 | Requirements Gathering & Analysis
2025-01-02 | Collect user requirements | High | Iter 1 | Done
2025-02-02 | Analyse requirements | High | Iter 2 | Done
2025-03-02 | Document requirements | Medium | Iter 2 | Done
3 | System Design
2025-01-03 | Architectural design | High | Iter 3 | Done
2025-02-03 | Usecase design | High | Iter 3 | Done
2025-03-03 | Database design | Medium | Iter 3 | Done
2025-04-03 | UI/UX design | High | Iter 3 | Done
4 | Documentation
2025-01-04 | Project Tracking | High | Iter 1 | Done
2025-02-04 | Project Introduction | Low | Iter 1 | Done
2025-03-04 | Project Management Plan | High | Iter 2 | Done
2025-04-04 | Software Requirements Specification | High | Iter 2 | Done
2025-05-04 | Software Design Description | High | Iter 3 | Done
2025-06-04 | Software Testing Document | Low | Iter 4 | Done
2025-07-04 | Software User Guides | Medium | Iter 5 | Done
2025-08-04 | Final Project Report | High | Iter 5 | Done
5 | Development
2025-01-05 | API Development
| Define Models | High | Iter 2 | Done
| Develop API Module Attendance | High | Iter 3 | Done
| Develop API Module Configuration | High | Iter 2 | Done
| Develop API Module Device | Medium | Iter 2 | Done
| Develop API Module FaceId | High | Iter 3 | Done
| Develop API Module Notification | Low | Iter 5 | Done
| Develop API Module Schedule | High | Iter 3 | Done
| Develop API Module User | High | Iter 3 | Done
| API Documentation | Low | Iter 2 | Done
| Deploy API | Medium | Iter 5 | Done
2025-02-05 | Website Development
| Develop for Module Attendance | Medium | Iter 5 | Done
| Develop for Module Configuration | High | Iter 3 | Done
| Develop for Module Device | Low | Iter 5 | Done
| Develop for Module FaceId | Low | Iter 3 | Done
| Develop for Module Notification | Medium | Iter 5 | Done
| Develop for Module Schedule | High | Iter 3 | Done
| Develop for Module User | High | Iter 3 | Done
2025-03-05 | Mobile Development
| Develop for Module Attendance | High | Iter 3 | Done
| Develop for Module Configuration | Medium | Iter 2 | Done
| Develop for Module Device | High | Iter 2 | Done
| Develop for Module FaceId | High | Iter 3 | Done
| Develop for Module Notification | Medium | Iter 5 | Done
| Develop for Module Schedule | Low | Iter 3 | Done
| Develop for Module User | Low | Iter 3 | Done
2025-04-05 | System Development

## Document
No | Report | Sections | Description | Level | Status | Assignees | Note
1 | 1. Project Introduction | 1. Overview | The Overview section provides a high-level summary of the project, outlining its purpose, objectives, and the problems it aims to address. This section introduces the project concept, target audience, and the core technologies involved, offering a snapshot of what the reader can expect from the document. It sets the stage for understanding the project's significance and relevance. | Low | Finished | Nguyễn Đình Dũng
2 |  | 2. Project Background | The Project Background section delves into the context and rationale behind the project. It discusses global and local trends relevant to the project, such as market demands, technological advancements, or industry-specific challenges. This section explains the motivation for undertaking the project and provides evidence-based statistics and facts to support the need for the proposed solution. | Low | Finished | Nguyễn Đình Dũng
3 |  | 3. Business Opportunities | The Business Opportunities section identifies potential benefits and market gaps that the project aims to address. It explores how the project can provide value to businesses, enhance operational efficiency, and cater to unmet user needs. This section also highlights the potential for scaling the project, its impact on relevant industries, and its alignment with current market trends. | Medium | Finished | Nguyễn Đình Dũng
4 |  | 4. Existing System | The Existing System section reviews current solutions or alternatives available in the market. It examines their strengths, weaknesses, and limitations, providing insights into why a new system is necessary. This section establishes a benchmark for the proposed project by comparing it to existing technologies and explaining how it intends to improve or differentiate itself. | Medium | Finished | Nguyễn Đình Dũng
5 |  | 5. Product Vision | The Product Vision section articulates the long-term goals and aspirations for the project. It defines what the product aims to achieve and its intended impact on users and the industry. This section outlines the core principles guiding the project's development, emphasizing innovation, usability, and scalability. It serves as a guiding light for the entire project lifecycle. | Medium | Finished | Nguyễn Đình Dũng
6 |  | 6. Project Scope & Limitation | The Project Scope & Limitation section defines the boundaries of the project, detailing what is included and excluded from the current release. It identifies key features, functionalities, and user groups targeted by the project, as well as any known constraints, such as technological, financial, or resource-related limitations. This section ensures clarity in expectations and provides a realistic roadmap for project delivery. | High | Finished | Nguyễn Đình Dũng
7 | 2. Project Management Plan | 1. Overview | The Overview section introduces the Project Management Plan, outlining its purpose and scope. It briefly explains how the plan will guide project execution, monitor progress, and ensure objectives are met within constraints such as time, budget, and quality. This section sets the context for the management strategy and the document structure. | Low | Finished | Nguyễn Đình Dũng
8 |  | 2. Management Approach | The Management Approach details the strategies and methodologies to be used for effective project management. It defines the project management framework (e.g., Agile, Waterfall, or Hybrid), highlights tools and techniques for tracking progress, and explains how risks will be identified, assessed, and mitigated. This section also outlines how changes to the project will be handled. | High | Finished | Nguyễn Đình Dũng
9 |  | 3. Project Deliverables | The Project Deliverables section lists all key outputs the project is expected to produce. Each deliverable is described in detail, along with its associated milestones and deadlines. This section ensures clarity on what will be delivered to stakeholders and serves as a benchmark for project success. | High | Finished | Nguyễn Đình Dũng
10 |  | 4. Responsibility Assignments | The Responsibility Assignments section defines the roles and responsibilities of team members. Using tools like a RACI (Responsible, Accountable, Consulted, Informed) matrix, it provides a clear understanding of who is responsible for specific tasks, decisions, and outcomes. This section ensures accountability and streamlines communication within the team. | High | Finished | Nguyễn Đình Dũng
11 |  | 5. Project Communication | The Project Communication section outlines the communication strategy for the project. It defines communication channels, frequencies, and methods for updates, meetings, and stakeholder interactions. This section ensures that all team members and stakeholders are informed, aligned, and engaged throughout the project lifecycle. | Medium | Finished | Nguyễn Đình Dũng
12 |  | 6. Configuration Management | The Configuration Management section focuses on maintaining the integrity and consistency of project deliverables. It details processes for version control, change tracking, and document management. This section ensures that all project assets are systematically managed to prevent confusion or duplication, especially in dynamic environments. | Low | Finished | Nguyễn Đình Dũng
13 | 3. Software Requirements Specification | 1. Overview | The Overview section introduces the purpose, scope, and objectives of the software. It provides context for the system being developed, outlines its intended audience, and highlights how it aligns with the overall project goals. This section also briefly describes the structure of the requirements specification document. | High | Finished | Kiều Thị Ngọc Dung
14 |  | 2. User Requirements | The User Requirements section focuses on what end-users need from the system. It describes specific goals, tasks, and features that the software must provide to meet user expectations. This section captures requirements in user-friendly terms, often using scenarios, user stories, or use cases, and avoids technical jargon to ensure clarity. | High | Finished | Kiều Thị Ngọc Dung
15 |  | 3.1. System Functional Overview | The System Functional Overview provides a high-level description of the system's primary functionalities. It outlines the main features and their purpose without going into detailed technical specifications. This section serves as a bridge between user requirements and detailed system functions. | High | Finished | Kiều Thị Ngọc Dung
16 |  | 3.1.5. Entity Relationship | The Entity Relationship subsection describes the logical structure of the system's data. It includes an ER diagram that illustrates how data entities are related to one another, defining the schema for the database and ensuring that data requirements are well understood and documented. | High | Finished | Kiều Thị Ngọc Dung
17 |  | 3.2.1. System Functional Details for Website | This subsection provides detailed functional specifications for the website. Each function is broken down to include its purpose, inputs, outputs, processes, and dependencies. Specific features like authentication, dashboard functionality, reporting, or third-party integrations are described in detail here. | High | Finished | Nguyễn Đình Dũng
18 |  | 3.2.2. System Functional Details for Mobile | This subsection provides detailed functional specifications for the mobile application. It defines the app's functionalities, including user authentication, push notifications, task automation features, and any device-specific integrations (e.g., camera or sensors). Each functionality is described with its inputs, outputs, and dependencies. | High | Finished | Kiều Thị Ngọc Dung
19 |  | 4. Non-functional Requirements | The Non-functional Requirements section outlines the quality attributes and constraints of the system. It includes specifications for performance, scalability, security, reliability, maintainability, and usability. This section ensures the system meets high standards of efficiency and user experience. | Medium | Finished | Kiều Thị Ngọc Dung
20 |  | 5. Requirement Appendix | The Requirement Appendix includes supplementary materials that support the requirements document. It may contain glossaries, references to standards or regulations, diagrams, or additional documentation to help stakeholders understand the requirements. | Low | Finished | Kiều Thị Ngọc Dung
21 | 4. Software Design Description | 1. System Design | The System Design section provides a high-level architectural view of the system. It includes diagrams and descriptions of how the system components interact with each other, defining the relationships and data flow between modules. This section outlines the core design principles, such as modularity, scalability, and maintainability, that guide the overall system architecture. | High | Finished | Nguyễn Văn Đạt
22 |  | 2. Database Design | The Database Design section focuses on the structure and schema of the database. It provides details about tables, relationships, constraints, and indexes. The section includes ER diagrams, normalization processes, and decisions made to ensure data integrity, efficiency, and scalability. It also highlights how the database aligns with the system’s data requirements. | High | Finished | Nguyễn Văn Đạt
23 |  | 3. Detailed Design | The Detailed Design for API subsection specifies how the backend APIs are structured and implemented. It describes the endpoints, request/response formats, authentication mechanisms, and data processing workflows. This section ensures that the APIs are secure, efficient, and aligned with both website and mobile app requirements. | High | Finished | Nguyễn Văn Đạt
26 |  | 4. Other Detailed Design | The Deployment Architecture section outlines how the system will be deployed and hosted. It includes descriptions of the server architecture, cloud services, CI/CD pipelines, and tools used for deployment. Diagrams illustrate the distribution of system components across servers and environments, emphasizing performance, security, and scalability. | High | Finished | Hà Việt Hiếu
27 | 5. Software Testing Document | 1. Scope of Testing | The Scope of Testing section defines the boundaries and focus areas of the testing process. It outlines what components, functionalities, and modules of the system will be tested, and clarifies any exclusions or limitations. This section ensures alignment between the testing team and stakeholders about what will and won’t be covered during testing. | Low | Finished | Nguyễn Đình Dũng
28 |  | 2. Test Strategy | The Test Strategy section provides a high-level approach to testing. It includes methodologies, tools, environments, and frameworks that will be used for testing. This section also describes testing types (e.g., functional, integration, regression, performance) and the criteria for success or acceptance. | Medium | Finished | Nguyễn Đình Dũng
29 |  | 3. Test Plan | The Test Plan section includes detailed scheduling, roles, and responsibilities for executing the tests. It specifies timelines, resources, and dependencies to ensure testing activities are properly coordinated and monitored. This section also identifies risks and mitigation strategies to handle potential testing roadblocks. | High | Finished | Nguyễn Đình Dũng
30 |  | 4. Test Cases | The Test Cases section contains specific scenarios designed to verify whether the system meets the defined requirements. Each test case includes a description, input conditions, expected outputs, and pass/fail criteria. This section provides detailed scripts or steps to be followed during execution, ensuring consistency and reproducibility. | Medium | Finished | Kiều Thị Ngọc Dung
31 |  | 5. Test Reports | The Test Reports section documents the results of the testing activities. It includes summaries of passed, failed, or skipped tests, bug reports, and metrics like defect density or test coverage. This section provides stakeholders with a clear picture of the system’s quality and readiness for deployment. | High | Finished | Kiều Thị Ngọc Dung
32 | 6. Software User Guides | 1. Delivarable Package | The Deliverable Package section outlines the final set of software artifacts that will be provided to the user or customer. It includes the software package itself, necessary installation files, configuration files, and any additional resources needed for the user to get started. This section ensures that all required components are packaged and ready for deployment. | Medium | Finished | Nguyễn Đình Dũng
33 |  | 2. Installation Guides | The Installation Guides section provides step-by-step instructions for setting up the software on the user’s system. This section covers system prerequisites, platform-specific setup details (e.g., Windows, macOS, Linux), and instructions for configuring the software, including any dependencies. The goal is to enable users to easily install and configure the software with minimal assistance. | Medium | Finished | Nguyễn Đình Dũng
34 |  | 3. User Manual | The User Manual is the core guide for interacting with the software. It provides comprehensive instructions on how to use the software, covering all major features and functionalities. This section includes user interface descriptions, workflows, and examples, helping users understand how to perform tasks and get the most out of the application. It also includes troubleshooting tips and FAQs to assist with common issues. | Medium | Finished | Nguyễn Đình Dũng | DungND (Website), DungKTN (App)
35 | 7. Final Project Report | Total combination of aboving documents | The Final Project Report is a comprehensive compilation of all key documents and findings from the entire project lifecycle. It integrates the various aspects of the project's development, from planning and design to implementation and testing, and provides a clear view of the work completed. | High | Finished | All

## Code
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | ID | Use case | Actor | Screen/Function Description | App | Web | API | Status | Planned | Updated | Update Details | Notes
1 | UC-01 | Sign In | Student, Lecturer, Admin | Login using registered credentials or linked OAuth account. | KhanhTL | DungND | DatNV | Done | Iter 2 | None
2 | UC-02 | Sign Out | Student, Lecturer, Admin | Securely sign out of the application. | KhanhTL | DungND | None | Done | Iter 4 | None
3 | UC-03 | View Student Setting | Student | View/manage settings: profile, notifications, device, FaceID, logout. | HieuHV | None | DatNV | Done | Iter 4 | None
4 | UC-04 | View Lecture Setting | Lecturer | View/manage settings: profile, notifications, device, logout. | HieuHV | None | DatNV | Done | Iter 4 | None
5 | UC-05 | View Profile | Student, Lecturer | Display user profile details. | KhanhTL | None | DatNV | Done | Iter 4 | None
6 | UC-06 | View Device | Student, Lecturer | View registered devices and update info. | KhanhTL | None | DatNV | Done | Iter 4 | None
7 | UC-07 | Register Device | Student, Lecturer | Register Bluetooth-capable devices for attendance. | HieuHV | None | DatNV | Done | Iter 2 | None
8 | UC-08 | View FaceID | Student, Lecturer | View and manage registered Face ID. | HieuHV | None | HieuHV | Done | Iter 3 | None
9 | UC-09 | Register Face ID | Student | Register facial data for secure login/attendance. | KhanhTL | None | HieuHV | Done | Iter 3 | None
10 | UC-10 | Update Face ID | Student | Update Face ID if already registered. | HieuHV | None | HieuHV | Done | Iter 3 | None
11 | UC-11 | View Student Home Page | Student | Display upcoming schedule and announcements. | HieuHV | None | DatNV | Done | Iter 4 | None
12 | UC-12 | View Student Schedule | Student | Show student timetable and sessions. | HieuHV | None | DatNV | Done | Iter 2 | None
13 | UC-13 | View Student Calendar | Student, Lecturer | View calendar format with classes and session details. | HieuHV | None | DatNV | Done | Iter 4 | None
14 | UC-14 | View Personal Attendance Report | Student | View attendance percentage per subject/semester. | KhanhTL | None | DatNV | Done | Iter 4 | None
15 | UC-15 | Backfill Data | System | Backfill offline data when reconnected. | KhanhTL | None | None | Done | Iter 3 | None
16 | UC-16 | Join Attendance Session | Student | Join an active roll call session. | KhanhTL | None | DatNV | Done | Iter 2 | None
17 | UC-17 | View Session Detail | Student | View session info, history, and final attendance. | KhanhTL | None | DatNV | Done | Iter 4 | None
18 | UC-18 | Verify FaceID Request | Student | Verify identity via Face ID during session. | HieuHV | None | HieuHV | Done | Iter 3 | None
19 | UC-19 | View Lecturer Home Page | Lecturer | Teaching overview: subjects, student stats, progress. | KhanhTL | None | DatNV | Done | Iter 2 | None
20 | UC-20 | View Lecturer Schedule | Lecturer | View teaching schedule and access sessions. | KhanhTL | None | DatNV | Done | Iter 2 | None
21 | UC-21 | View Lecturer Calendar | Lecturer | Calendar of scheduled classes and activities. | KhanhTL | None | DatNV | Done | Iter 5 | None
22 | UC-22 | View Lecturer Session Detail | Lecturer | Detailed session info: history, total duration, stats. | KhanhTL | None | DatNV | Done | Iter 2 | None
23 | UC-23 | View Class Attendance Report | Lecturer | View class-level attendance summaries. | KhanhTL | None | DatNV | Done | Iter 2 | None
24 | UC-24 | View Session Attendance Report | Lecturer | View detailed report of each session. | KhanhTL | None | DatNV | Done | Iter 2 | None
25 | UC-25 | Broadcast and Scan Signal | Student, Lecturer | Start Bluetooth scan to trigger attendance. | KhanhTL | None | DatNV | Done | Iter 2 | None
26 | UC-26 | Create FaceID Request | Lecturer | Request Face ID verification during the session. | HieuHV | None | HieuHV | Done | Iter 4 | None
27 | UC-27 | Automotive Attendance | Lecturer | Auto-take attendance via Bluetooth. | HieuHV | None | DatNV | Done | Iter 2 | None
28 | UC-28 | Manual Attendance | Lecturer | Mark attendance manually (within 24h). | KhanhTL | None | DatNV | Done | Iter 3 | None
29 | UC-29 | Start Attendance Session | Lecturer | Start a new attendance session (manual/auto). | KhanhTL | None | DatNV | Done | Iter 2 | None
30 | UC-30 | View Dashboard | Admin | Provide an overview of key statistics, schedules, and summary cards, charts, and highlights. | None | DungKTN | DatNV | Done | Iter 4 | None
31 | UC-31 | View Rooms | Admin | Admin views all rooms with search, filter, and pagination. | None | DungKTN | DatNV | Done | Iter 3 | None
32 | UC-32 | Add Room | Admin | Admin adds a new room (name, building, capacity, status). | None | DungKTN | DatNV | Done | Iter 2 | None
33 | UC-33 | Edit Room | Admin | Admin edits an existing room’s details. | None | DungKTN | DatNV | Done | Iter 3 | None
34 | UC-34 | Delete Room | Admin | Admin deletes a room (if not referenced or with safe checks). | None | DungKTN | DatNV | Done | Iter 3 | None
35 | UC-35 | View Courses | Admin | Admin views all courses with search/filter. | None | DungKTN | DatNV | Done | Iter 3 | None
36 | UC-36 | Add Course | Admin | Admin creates a new course (code, name, description, semester). | None | DungKTN | DatNV | Done | Iter 2 | None
37 | UC-37 | Edit Course | Admin | Admin updates course information. | None | DungKTN | DatNV | Done | Iter 3 | None
38 | UC-38 | Delete Course | Admin | Admin deletes a course (with dependency validation). | None | DungKTN | DatNV | Done | Iter 3 | None
39 | UC-39 | View Classes | Admin | Admin views all classes (by course/semester/lecturer). | None | DungKTN | DatNV | Done | Iter 3 | None
40 | UC-40 | Edit Class | Admin | Admin edits class info (lecturer, section, schedule links). | None | DungKTN | DatNV | Done | Iter 3 | None
41 | UC-41 | Delete Class | Admin | Admin deletes a class (respecting constraints/history). | None | DungKTN | DatNV | Done | Iter 3 | None
42 | UC-42 | Add Class | Admin | Admin adds a new class and links it to a course/semester. | None | DungKTN | DatNV | Done | Iter 2 | None
43 | UC-43 | View Class Details | Admin | Admin views detailed class info (students, sessions, stats). | None | DungKTN | DatNV | Done | Iter 3 | None
44 | UC-44 | Assign Lecturer | Admin | Admin assigns a lecturer to a class (or reassigns). | None | DungND | DatNV | Done | Iter 3 | None
45 | UC-45 | View Enrolled Student | Admin | Admin views enrolled students of a class. | None | DungND | DatNV | Done | Iter 3 | None
46 | UC-46 | Import Student | Admin | Admin imports students in bulk (e.g., CSV/Excel). | None | DungND | DatNV | Done | Iter 3 | None
47 | UC-47 | Enroll Student | Admin | Admin enrolls a student into a class. | None | DungND | DatNV | Done | Iter 2 | None
48 | UC-48 | View Schedules | Admin | Admin views all schedules (filters by room/class/date). | None | DungND | DatNV | Done | Iter 3 | None
49 | UC-49 | Add Schedule | Admin | Admin creates a schedule entry (time, room, class). | None | DungND | DatNV | Done | Iter 2 | None
50 | UC-50 | Edit Schedule | Admin | Admin edits a schedule entry. | None | DungND | DatNV | Done | Iter 3 | None
51 | UC-51 | Delete Schedule | Admin | Admin deletes a schedule entry. | None | DungND | DatNV | Done | Iter 3 | None
52 | UC-52 | View Sessions | Admin | Admin views sessions (planned and completed). | None | DungND | DatNV | Done | Iter 4 | None
53 | UC-53 | Edit Session | Admin | Admin edits a session (time/room/status/notes). | None | DungND | DatNV | Done | Iter 4 | None
54 | UC-54 | Delete Session | Admin | Admin deletes a session (with audit constraints). | None | DungND | DatNV | Done | Iter 4 | None
55 | UC-55 | View Session Details | Admin | Admin views session details (attendance list, metrics). | None | DungND | DatNV | Done | Iter 4 | None
56 | UC-56 | Edit Attendance | Admin | Admin edits attendance records for a session (audited). | None | DungND | DatNV | Done | Iter 5 | None
57 | UC-57 | View Users | Admin | Admin views users (students/lecturers/admins) with filters. | None | DungND | DatNV | Done | Iter 3 | None
58 | UC-58 | Add User | Admin | Admin adds a new user account. | None | DungND | DatNV | Done | Iter 2 | None
59 | UC-59 | Import User | Admin | Admin imports users in bulk (CSV/Excel). | None | DungND | DatNV | Done | Iter 3 | None
60 | UC-60 | Edit User | Admin | Admin edits user information (name, email, role, etc.). | None | DungND | DatNV | Done | Iter 3 | None
61 | UC-61 | Change User Status | Admin | Admin changes a user’s status (activate/deactivate/lock). | None | DungND | DatNV | Done | Iter 5 | None
62 | UC-62 | View User Details | Admin | Admin views detailed user profile and activity. | None | DungND | DatNV | Done | Iter 5 | None
63 | UC-63 | View Active Devices | Admin | Admin views active devices linked to users. | None | DungND | DatNV | Done | Iter 5 | None
64 | UC-64 | Inactive Device | Admin | Admin marks a device as inactive/disabled. | None | DungND | DatNV | Done | Iter 4 | None
65 | UC-65 | View Device Requests | Admin | Admin views incoming device registration requests. | None | DungND | DatNV | Done | Iter 5 | None
66 | UC-66 | Edit Device Request | Admin | Admin reviews and updates a device request (approve/reject, notes). | None | DungND | DatNV | Done | Iter 5 | None
67 | UC-67 | View Active FaceIDs | Admin | Admin views active FaceIDs (approved/usable records). | None | DungND | HieuHV | Done | Iter 4 | None
68 | UC-68 | View Attribute Definitions | Admin | Admin views attribute definitions used by the system. | None | DungND | DatNV | Done | Iter 3 | None
69 | UC-69 | Create Attribute Definition | Admin | Admin creates a new attribute definition. | None | DungND | DatNV | Done | Iter 2 | None
70 | UC-70 | Update Attribute Definition | Admin | Admin updates an existing attribute definition. | None | DungND | DatNV | Done | Iter 3 | None
71 | UC-71 | Delete Attribute Definition | Admin | Admin deletes an attribute definition (with validation). | None | DungND | DatNV | Done | Iter 5 | None
72 | UC-72 | View Settings | Admin | Admin views global/system settings. | None | DungND | DatNV | Done | Iter 3 | None
73 | UC-73 | Create Setting | Admin | Admin creates a new setting (key/value or structured). | None | DungND | DatNV | Done | Iter 2 | None
74 | UC-74 | Update Setting | Admin | Admin updates an existing setting. | None | DungND | DatNV | Done | Iter 3 | None
75 | UC-75 | Delete Setting | Admin | Admin deletes a setting (with safety checks). | None | DungND | DatNV | Done | Iter 5 | None
76 | UC-76 | Process Attendance Data | System | Validate and store submitted attendance records. | None | None | DatNV | Done | Iter 2 | None
77 | UC-77 | Store Local Attendance Data | System (Mobile) | Temporarily store attendance offline when the device is disconnected. | KhanhTL | None | None | Done | Iter 2 | None

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
Register Device | Screen Schedule | DungKTN | Thiết bị chưa đăng kí device ( cả lecture + cả student ) vẫn join lớp học được | KhanhTL | Closed
Join Session | Screen Schedule | DungKTN | Tiết gọc bắt đầu , giảng viên chưa join lớp nên hs cũng chưa join lớp nhưng màn hình sau khi quá giờ tiết học vẫn hiện Upcoming | KhanhTL | Closed
Report | Screen Report | DungKTN | Tính trạng session lặp lại nhiều lần trong report ( kh biết do lỗi hay đặt tên cần giải thích | KhanhTL | Closed
Device | Screen Device | DungKTN | Lecture vẫn còn màn Update Device | KhanhTL | Closed
Home | Screen Home | DungKTN | Giao diện home vẫn đang được hash cứng tên người dùng | KhanhTL | Closed
Sessions | Screen Sessions | DungKTN | Trả vè No data attend khi tắt bluetooth ngay từ đầu khi bắt đầu quét | KhanhTL | Closed
Sessions | Screen Sessions | DungKTN | Check lại Count điểm danh ( bên ngoài khác bên trong) | KhanhTL | Closed
Sessions | Screen Sessions | DungKTN | Bên ngoài 20 sessions ( bên trong 42 session - students ) | KhanhTL | Closed
Attendance | Screen Attendance | DungKTN | Tính toán điểm danh bên ngoài round count = 0 bên trong round đã attend | KhanhTL | Closed
Attendance | Screen Profile | DungKTN | Đổi account Mô tả : Student 1 sử dụng account 1 đăng kí device 1 Student 1 sử dụng account 2 của stu 2 để điểm danh -> Kết quả student 1 đc điểm danh , stu 2 không | KhanhTL | Closed